## Client Gantt Chart
| PROJECT NAME | PROJECT SUPERVISOR | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 1. ML Tool 2. Code 3. Final Report
| Tytonidae Tympanometry | Robyn Choi | 2021-07-26 | 2021-10-22 |  | 20% |  | TEAM MEMBERS | Daniel Chegwidden, Cheng Nian, Karan Rebello, Aminul Islam, Anitha Raghupathy, Di Yao
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
| Initial Client Meeting |  |  |  | 2021-08-05 | 2021-08-05 | 0 | Completed |  | Complete
| Propject Proposal |  |  |  | 2021-08-05 | 2021-08-19 | 14 | In Progress |  | Overdue
| Data Preprocessing |  |  |  | 2021-07-29 | 2021-08-19 | 21 | In Progress |  | In Progress
| Second Client Meeting |  |  |  | 2021-08-19 | 2021-08-19 | 0 | Not Started
| Data Modelling |  |  |  | 2021-08-14 | 2021-09-29 | 46 | Not Started
| Third Client Meeting |  |  |  | 2021-09-30 | 2021-09-30 | 0 | Not Started
| Review |  |  |  | 2021-10-01 | 2021-10-07 | 6 | Not Started
| Fourth Client Meeting |  |  |  | 2021-10-14 | 2021-10-14 | 0 | Not Started
| Model Deployment |  |  |  | 2021-10-08 | 2021-10-12 | 4 | Not Started
| Testing |  |  |  | 2021-10-13 | 2021-10-20 | 7 | Not Started
| Final Report |  |  |  | 2022-10-08 | 2022-10-22 | 14 | Not Started

## Team Gantt Chart
| PROJECT NAME | PROJECT SUPERVISOR | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 1. ML Tool 2. Code 3. Final Report
| Tytonidae Tympanometry | Robyn Choi | 2021-07-26 | 2021-10-22 |  | 20% |  | TEAM MEMBERS | Daniel Chegwidden, Cheng Nian, Karan Rebello, Aminul Islam, Anitha Raghupathy, Di Yao
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
| Introductory Team meeting |  |  |  | 2021-07-28 | 2021-07-28 | 0 | Completed | Meeting the team | Complete
| Progress meeting 1 |  |  |  | 2021-08-02 | 2021-08-02 | 0 | In Progress | Set up GitHub | Overdue
| Data Procesing - subteam |  |  |  | 2021-08-05 | 2021-08-12 | 7 | Complete |  | In Progress
| Proposal draft - subteam |  |  |  | 2021-08-05 | 2021-08-12 | 7 | In Progress
| Progress meeting 2 |  |  |  | 2021-08-09 | 2021-08-09 | 0 | Complete | Check-on each team's work progress
| Finalise Proposal |  |  |  | 2021-08-12 | 2021-08-19 | 7 | In Progress
| Seek feedback from client |  |  |  | 2021-08-19 | 2021-08-19 | 0 | Not Started
| Data Modelling |  | all members within paris |  | 2021-08-14 | 2021-09-29 | 46 | Not Started
| Model Evaluation |  | all members within paris |  | 2021-09-20 | 2021-10-12 | 22 | Not Started
| Final Report |  |  |  | 2022-10-01 | 2022-10-22 | 21 | Not Started