## Client Gantt Chart
PROJECT NAME | PROJECT SUPERVISOR | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 1. ML Tool 2. Code 3. Final Report
Tytonidae Tympanometry | Robyn Choi | 2021-07-26 | 2021-10-22 |  | 23.08% |  | TEAM MEMBERS | Daniel Chegwidden, Cheng Nian, Karan Rebello, Aminul Islam, Anitha Raghupathy, Di Yao
TASK NAME |  | RESPONSIBLE |  | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
Phase 1 |  |  |  | 2021-07-26 | 2021-08-20 | 25 | In Progress | Team A - Karan, Di, Anitha Team B - Daniel, Cheng, Aminul Team Leader - Daniel | Complete
Client Meeting 1 |  | Team Leader |  | 2021-07-28 | 2021-07-28 | 0 | Completed |  | Overdue
Proposal Draft |  | Team A |  | 2021-08-05 | 2021-08-12 | 7 | Completed |  | In Progress
Data Preprocessing |  | Team B |  | 2021-08-05 | 2021-08-12 | 7 | Completed
Proposal Draft |  | Team B |  | 2021-08-13 | 2021-08-20 | 7 | Complete
Data Preprocessing |  | Team A |  | 2021-08-13 | 2021-08-20 | 7 | In Progress
Client Meeting 2 |  | Team Leader |  | 2021-08-19 | 2021-08-19 | 0 | Complete
Phase 2 |  |  |  | 2021-08-21 | 2021-09-24 | 34 | Not Started
Machine Learning Modelling |  | Entire Team |  | 2021-08-21 | 2021-09-24 | 34 | Not Started
Client Meeting 3 |  | Team Leader |  | 2021-09-02 | 2021-09-02 | 0 | Not Started
Model Proposal and Selection |  | Entire Team |  | 2021-09-13 | 2021-09-24 | 11 | Not Started
Client Meeting 4 |  | Team Leader |  | 2021-09-16 | 2021-09-16 | 0 | Not Started
Phase 3 |  |  |  | 2021-09-25 | 2021-10-22 | 27 | Not Started
Result Analysis |  | Team C |  | 2021-09-25 | 2021-10-08 | 13 | Not Started
Result Visualization |  | Team D |  | 2021-09-25 | 2021-10-08 | 13 | Not Started
Client Meeting 5 |  | Team Leader |  | 2021-09-30 | 2021-09-30 | 0 | Not Started
Final Report |  | Team E |  | 2021-10-01 | 2021-10-22 | 21 | Not Started
Client Meeting 6 |  | Team Leader |  | 2021-10-14 | 2021-10-14 | 0 | Not Started

## Team Gantt Chart
PROJECT NAME | PROJECT SUPERVISOR | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 1. ML Tool 2. Code 3. Final Report
Tytonidae Tympanometry | Robyn Choi | 2021-07-26 | 2021-10-22 |  | 17.39% |  | TEAM MEMBERS | Daniel Chegwidden, Cheng Nian, Karan Rebello, Aminul Islam, Anitha Raghupathy, Di Yao
TASK NAME |  | RESPONSIBLE |  | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
Phase 1 |  |  |  | 2021-07-26 | 2021-08-20 | 25 | In Progress | Team A - Karan, Di, Anitha Team B - Daniel, Cheng, Aminul Team Leader - Daniel | Complete
Developer Meeting 1 |  | Team Leader |  | 2021-07-28 | 2021-07-28 | 0 | Completed |  | Overdue
Developer Meeting 2 |  | Team Leader |  | 2021-08-02 | 2021-08-02 | 0 | Completed |  | In Progress
Proposal Draft |  | Team A |  | 2021-08-05 | 2021-08-12 | 7 | Completed
Data Preprocessing |  | Team B |  | 2021-08-05 | 2021-08-12 | 7 | Completed
Client Meeting 1 |  | Team Leader |  | 2021-08-05 | 2021-08-05 | 0 | Complete
Developer Meeting 3 |  | Team Leader |  | 2021-08-09 | 2021-08-09 | 0 | Complete
Proposal Draft |  | Team B |  | 2021-08-13 | 2021-08-20 | 7 | Complete
Data Preprocessing |  | Team A |  | 2021-08-13 | 2021-08-20 | 7 | In Progress
Developer Meeting 4 |  | Team Leader |  | 2021-08-16 | 2021-08-16 | 0 | Complete
Client Meeting 2 |  | Team Leader |  | 2021-08-19 | 2021-08-19 | 0 | Complete
Phase 2 |  |  |  | 2021-08-21 | 2021-09-24 | 34 | Not Started
Machine Learning Modelling |  | Entire Team |  | 2021-08-21 | 2021-09-24 | 34 | Not Started
Developer Meeting 5 |  | Team Leader |  | 2021-08-23 | 2021-08-23 | 0 | Not Started
Developer Meeting 6 |  | Team Leader |  | 2021-08-30 | 2021-08-30 | 0 | Not Started
Client Meeting 3 |  | Team Leader |  | 2021-09-02 | 2021-09-02 | 0 | Not Started
Developer Meeting 7 |  | Team Leader |  | 2021-09-06 | 2021-09-06 | 0 | Not Started
Developer Meeting 8 |  | Team Leader |  | 2021-09-13 | 2021-09-13 | 0 | Not Started
Model Proposal and Selection |  | Entire Team |  | 2021-09-13 | 2021-09-24 | 11 | Not Started
Client Meeting 4 |  | Team Leader |  | 2021-09-16 | 2021-09-16 | 0 | Not Started
Developer Meeting 9 |  | Team Leader |  | 2021-09-20 | 2021-09-20 | 0 | Not Started
Phase 3 |  |  |  | 2021-09-25 | 2021-10-22 | 27 | Not Started
Result Analysis |  | Team C |  | 2021-09-25 | 2021-10-08 | 13 | Not Started
Result Visualization |  | Team D |  | 2021-09-25 | 2021-10-08 | 13 | Not Started
Developer Meeting 10 |  | Team Leader |  | 2021-09-27 | 2021-09-27 | 0 | Not Started
Client Meeting 5 |  | Team Leader |  | 2021-09-16 | 2021-09-16 | 0 | Not Started
Final Report |  | Team E |  | 2021-10-01 | 2021-10-22 | 21 | Not Started
Developer Meeting 11 |  | Team Leader |  | 2021-10-04 | 2021-10-04 | 0 | Not Started
Client Meeting 4 |  | Team Leader |  | 2021-10-07 | 2021-10-07 | 0 | Not Started
Developer Meeting 12 |  | Team Leader |  | 2021-10-11 | 2021-10-11 | 0 | Not Started
Client Meeting 6 |  | Team Leader |  | 2021-09-16 | 2021-09-16 | 0 | Not Started
Developer Meeting 13 |  | Team Leader |  | 2021-10-18 | 2021-10-18 | 0 | Not Started