## Agile Project w Gantt
| PROJECT NAME | PROJECT SUPERVISOR | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | 1. ML Tool 2. Code 3. Final Report
| Product TyTy | Robyn Choi | 2021-08-05 | 2021-10-22 |  | 20% |  | TEAM MEMBERS | Daniel, Cheng, Di, Aminul, Anitha
AT RISK | TASK NAME |  | RESPONSIBLE |  | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
| Initial Client Meeting |  |  |  | 2021-08-05 | 2021-08-05 | 0 | Complete |  | Complete
| Project Proposal |  | Di, Karan, Anitha |  | 2021-08-05 | 2021-08-19 | 14 | In Progress |  | Overdue
| Data Preprocessing |  | Daniel, Cheng, Aminul |  | 2022-08-05 | 2022-08-13 | 8 | In Progress |  | In Progress
| Second Client Meeting |  |  |  | 2021-08-19 | 2021-08-19 | 0 | Not Started
| Data Modelling |  | All |  | 2021-08-14 | 2021-09-29 | 46 | Not Started
| Third Client Meeting |  |  |  | 2021-09-30 | 2021-09-30 | 0 | Not Started
| Review |  |  |  | 2021-10-01 | 2021-10-07 | 6 | Not Started
| Fourth Client Meeting |  |  |  | 2021-10-14 | 2021-10-14 | 0 | Not Started
| Model Deployment |  |  |  | 2021-10-08 | 2021-10-12 | 4 | Not Started
| Testing |  |  |  | 2021-10-13 | 2021-10-15 | 2 | Not Started
| Video Presentation |  |  |  | 2021-10-16 | 2021-10-22 | 6 | Not Started
| Final Report |  |  |  | 2022-10-08 | 2022-10-22 | 14 | Not Started

## Agile Project w Gantt BLANK
AGILE PROJECT with GANTT TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS | STATUS
| Sprint 1 | [5 empty] | 0 |  |  | Complete
| Feature 1 | [5 empty] | 0 |  |  | Overdue
| Feature 2 | [5 empty] | 0 |  |  | In Progress
| Feature 3 | [5 empty] | 0 |  |  | Not Started
| Sprint 2 | [5 empty] | 0
| Feature 4 | [5 empty] | 0
| Feature 5 | [5 empty] | 0
| Feature 6 | [5 empty] | 0
| Sprint 3 | [5 empty] | 0
| Feature 7 | [5 empty] | 0
| Feature 8 | [5 empty] | 0
| Feature 9 | [5 empty] | 0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.